## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Buyer | Access the website/app | I Can see the product listing | 1 | RP
1 | SB1/US2 | Buyer | See all the products | I Can see the variety of the products | 1 | VK
1 | SB1/US3 | Buyer | Search the product through search bar | I Can Search the choice of product by keyword | 1 | RB
1 | SB1/US4 | Buyer | View The Cart | I Can See The Products which are available in my cart | 1 | DM
1 | SB1/US5 | Buyer | Login | I can see my saved content | 1 | RJ
1 | SB1/US6 | Buyer | Signup | I Can start purchasing the product | 1 | PM
1 | SB1/US7 | Buyer | Contact to service provider | I can send a query | 1 | DM
1 | SB1/US8 | Buyer | See the product category wise | I Can see the product category wise | 1 | RJ
1 | SB1/US9 | Buyer | to add a product in my cart | I Can place a order | 1 | PM
1 | SB1/US10 | Buyer | to update a product quantity inside a cart | I Can change the quantity of the product in cart | 1 | DM
1 | SB1/US11 | Buyer | to delete a product inside a cart | I can remove the product from cart | 1 | DM
1 | SB1/US12 | Buyer | to see the cart total | I Can See the total amount of product which I have added in cart | 1 | RJ
1 | SB1/US13 | Buyer | to See the specific product detail | I Can check the details of the specific product | 1 | PM
1 | SB1/US14 | Buyer | to go to checkout | I Can select type of method of delivery | 1 | DM
1 | SB1/US15 | Buyer | See the order summery at checkout page | I Can see the products which I have added in cart | 1 | RJ
2 | SB2/US1 | Buyer | select the self pickup option | I Can select pickup delivery option | 1 | PM
2 | SB2/US2 | Buyer | select address from saved addresses | I Can select delivered to this address option | 1 | DM
2 | SB2/US3 | Buyer | add new delivery address | I Can add new address | 1 | RJ
2 | SB2/US4 | Buyer | place a order | I can get the product
2 | SB2/US5 | Buyer | see the thank you page | I Can assure my product confirmation | 1 | PM
2 | SB2/US6 | Buyer | receive the order details in main | I have a proof of order | 1 | DM
2 | SB2/US7 | Buyer | Remove product from cart | I Can delete the product from cart if no longer required | 1 | RJ
2 | SB2/US8 | Buyer | See the sub total of each item | I Can see the cost of each item | 1 | PM
2 | SB2/US9 | Buyer | See the banner area at home page | I Can see the special offers | 1 | DM
2 | SB2/US10 | Buyer | See the logout button | I Can logout from the website | 1 | DM
2 | SB2/US11 | Buyer | See the hot offers on home page | I Can see the currently running offer in the store | 1 | DM
2 | SB2/US12 | DBA | Create database | I Can store all customer information to serve customer better | 1 | DM
2 | SB2/US13 | DBA | Fire Select Queries | I Can View The Records | 1 | DM
2 | SB2/US14 | DBA | Fire Update Queries | I Can Keep The Database Updated | 1 | RJ
2 | SB2/US15 | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data | 1 | PM
3 | SB3/US1 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use | 1 | DM
3 | SB3/US2 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 1 | RJ
3 | SB3/US3 | Admin | Login Into The System Using given credentials | I Can Access The Admin panel | 2 | PM
3 | SB3/US4 | Admin | See the error in login | I Can Enter the correct credentials | 2 | DM
3 | SB3/US5 | Admin | See the homepage of admin panel | I can access the general content of admin
3 | SB3/US6 | Admin | See list of all the orders | I can prepare the order | 2 | RJ
3 | SB3/US7 | Admin | See the specific items ordered | I can prepare order specifically | 2 | PM
3 | SB3/US8 | Admin | See the total amount to be collected | I can collect that amount from customer at the time of delivery | 2 | DM
3 | SB3/US9 | Admin | See the type of order | I Can deliver the order accordingly | 2 | RJ
3 | SB3/US10 | Admin | See all the products present in database | I can update the details | 2 | PM
3 | SB3/US11 | Admin | Filter the product category wise | I Can see the products of particular category | 2 | DM
3 | SB3/US12 | Admin | Edit product details | Customer can see the latest details of the product | 2 | RJ
3 | SB3/US13 | Admin | Delete the product from the database | Customer cannot see the unwanted product | 2 | PM
3 | SB3/US14 | Admin | See the successfully updated message after product updated sucessfully | I Can assure that product details is updated | 2
3 | SB3/US15 | Admin | See the successfully deleted message after product deleted sucessfully | I Can assure that product is deleted from the database | 2
4 | SB4/US1 | Admin | Add a new product | Customer can see the newly added product | 2
4 | SB4/US2 | Admin | Upload image of the product | Customer can see the image of the newly added product also | 2
4 | SB4/US3 | Admin | See the successfully added product message after product added sucessfully | I Can assure that product is added in database | 2
4 | SB4/US4 | Admin | Add new category | I can add products in that category | 3
4 | SB4/US5 | Admin | See the successfully added category message after category added sucessfully | I Can assure that category is added in database | 3
4 | SB4/US6 | Admin | Delete category | Category is no longer visible in the website/app | 3
4 | SB4/US7 | Admin | See the successfully deleted category message after category deleted sucessfully | I Can assure that category is deleted from database | 3
4 | SB4/US8 | Admin | All the users in the website | I can see the list of users | 3
4 | SB4/US9 | Developer | Create android project | I can develop webview | 3
4 | SB4/US10 | Developer | create Webview in android application project | I can develop application | 3
4 | SB4/US11 | Developer | create Splash screen | Customer do not see blank page | 3
4 | SB4/US12 | Developer | Upload the android application to playstore | User can download the application
4 | SB4/US13 | Buyer | Install the android application | I Can do all the work in android phone | 3
4 | SB4/US14 | Buyer | Order the product via android application | I Can order the product by mobile | 3

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - All In One Grocery
SB1/US1 | Aa a Buyer I want to access the website/app so that I Can see the product listing | SB1/US1/T1 | Create A Website/App | RS | Completed | 23/9/2019
|  | SB1/US1/T2 | Design product list page | VK | Completed | 23/9/2019
|  | SB1/US1/T3 | Connection with database to fetch record | RB | Completed | 23/9/2019
|  | SB1/US1/T4 | List the product to front end | RS+RB+VK | Completed | 23/9/2019
|  | SB1/US1/T5 | Testing of the module | RS | Completed | 23/9/2019
SB1/US2 | Aa a Buyer I want to see all the product so that I can see the variety of the products | SB1/US2/T1 | Design product list page category wise | VK | Completed | 23/9/2019
|  | SB1/US2/T2 | Connection with database to fetch record | RB | Completed | 23/9/2019
|  | SB1/US2/T3 | List the product to front end category wise | RS+RB+VK | Completed | 23/9/2019
|  | SB1/US2/T4 | Testing of the module | RS+RB+VK | Completed | 23/9/2019
SB1/US3 | Aa a Buyer I want to search the product through search bar so that I can search the choice of product by keyword | SB1/US3/T1 | Design the search bar to enter the keyword | RS | Completed | 23/9/2019
|  | SB1/US3/T2 | Validate user input at Client Level & server level. | VK | Completed | 23/9/2019
|  | SB1/US3/T3 | Connection with database to fetch record according to keyword | RB | Completed | 23/9/2019
|  | SB1/US3/T4 | Testing of the module | RS+RB+VK | Completed | 23/9/2019
SB1/US4 | Aa a Buyer I want to View the cart so that I can see the products which are available in my cart | SB1/US4/T1 | Understanding the cart.js library | RS | Completed | 23/9/2019
|  | SB1/US4/T2 | Show the cart with a click of view cart button | VK | Completed | 23/9/2019
|  | SB1/US4/T3 | Show cart when a new product is added into cart | RB | Completed | 23/9/2019
|  | SB1/US4/T4 | Calculate the subtotal of the cart | RS+RB+VK | Completed | 23/9/2019
|  | SB1/US4/T5 | Testing of the module | RS+RB+VK | Completed | 23/9/2019
SB1/US5 | Aa a Buyer I want to Login so that I can see my saved content | SB1/US5/T1 | Designing the Login page | RS | Completed | 23/9/2019
|  | SB1/US5/T2 | Validate user input at Client Level & server level. | VK | Completed | 23/9/2019
|  | SB1/US5/T3 | Connection with database to check the authenticity of the user | RB | Completed | 23/9/2019
|  | SB1/US5/T4 | Logging in the user if Email Id and password is correct | RS+RB+VK | Completed | 23/9/2019
|  | SB1/US5/T5 | Display error in case Email Id or password is incorrect | RS | Completed | 23/9/2019
|  | SB1/US5/T6 | Testing of the module | VK | Completed | 23/9/2019
SB1/US6 | Aa a Buyer I want to Signup so that I start purchasing the product | SB1/US6/T1 | Designing the Signup page | RB | Completed | 23/9/2019
|  | SB1/US6/T2 | Validate user input at Client Level & server level. | RS+RB+VK | Completed | 23/9/2019
|  | SB1/US6/T3 | Connection with database to insert the data | RS+RB+VK | Completed | 23/9/2019
|  | SB1/US6/T4 | Signing up the user to homepage | RS | Completed | 23/9/2019
|  | SB1/US6/T5 | Testing of the module | VK | Completed | 23/9/2019
SB1/US7 | Aa a Buyer I want to contact the service provider so that I can send a query | SB1/US7/T1 | Designing of Contact us page | RB | Completed | 30/9/2019
|  | SB1/US7/T2 | Validate user input at Client Level & server level. | RS+RB+VK | Completed | 30/9/2019
|  | SB1/US7/T3 | Connection with database to insert the data | RS | Completed | 30/9/2019
|  | SB1/US7/T4 | Testing of the module | VK | Completed | 30/9/2019
SB1/US8 | Aa a Buyer I want to see the product category wise so that I can see the products category wise | SB1/US8/T1 | Designing the Product page | RB | Completed | 30/9/2019
|  | SB1/US8/T2 | Connection with database to fetch the product category wise | RS+RB+VK | Completed | 30/9/2019
|  | SB1/US8/T3 | Displaying the product dynamically | RS+RB+VK | Completed | 30/9/2019
|  | SB1/US8/T4 | Testing of the module | RS | Completed | 30/9/2019
SB1/US9 | Aa a Buyer I want to add a product in my cart so that I can place a order | SB1/US9/T1 | Adding product in cart Using cart.js | VK | Completed | 2019-05-10
|  | SB1/US9/T2 | Displaying total in cart | RB | Completed | 2019-05-10
|  | SB1/US9/T3 | Testing of the module | RS+RB+VK | Completed | 2019-05-10
SB1/US10 | Aa a Buyer I want to update a product quantity inside a cart so that I can change the quantity of the product in cart | SB1/US10/T1 | Update product quantity in cart Using cart.js | RS | Completed | 2019-05-10
|  | SB1/US10/T2 | Update cart product quantity and total amount | VK | Completed | 2019-05-10
|  | SB1/US10/T3 | Testing of the module | RB | Completed | 2019-05-10
SB1/US11 | Aa a Buyer I want to delete a product inside a cart so that I can remove the product from cart | SB1/US11/T1 | Delete product from cart Using cart.js | RS+RB+VK | Completed | 2019-05-10
|  | SB1/US11/T2 | Update cart and total amount | RS+RB+VK | Completed | 2019-05-10
|  | SB1/US11/T3 | Testing of the module | RS | Completed | 2019-05-10
SB1/US12 | Aa a Buyer I want to see the cart total so that I can see the total amount of product which I have added in cart | SB1/US12/T1 | Displaying total amount in cart Using cart.js | VK | Completed | 2019-05-10
|  | SB1/US12/T2 | Designing the display laout | RB | Completed | 2019-05-10
|  | SB1/US12/T3 | Testing of the module | RS+RB+VK | Completed | 2019-05-10
SB1/US13 | Aa a Buyer I want to see the specific product detail so that I can check the details of the specific product | SB1/US13/T1 | Designing the Product detail page | RS | Completed | 2019-05-10
|  | SB1/US13/T2 | Connection with database to fetch particular product details | VK | Completed | 2019-05-10
|  | SB1/US13/T3 | Displaying the particular product inside a page dynamically | RB | Completed | 2019-05-10
|  | SB1/US13/T4 | Testing of the module | RS+RB+VK | Completed | 2019-05-10
SB1/US14 | Aa a Buyer I want to go to checkout page so that I can select type of delivery | SB1/US14/T1 | Designing the Checkout page | RS+RB+VK | Completed | 2019-07-10
|  | SB1/US14/T2 | Fetching products details from cart | RB | Completed | 2019-07-10
|  | SB1/US14/T3 | Displaying the products fetched from cart | VK | Completed | 2019-07-10
|  | SB1/US14/T4 | Calculating the total amount with delivery charge | RS+RB+VK | Completed | 2019-07-10
|  | SB1/US14/T5 | Testing of the module | RB | Completed | 2019-07-10
SB1/US15 | Aa a Buyer I want to see the order summary at the checkout page so that I can see the products which I have added in cart | SB1/US15/T1 | Calculating order summary | RS+RB+VK | Completed | 2019-07-10
|  | SB1/US15/T2 | Calculating total cost according to products added by buyer | RB | Completed | 2019-07-10
|  | SB1/US15/T3 | Testing of the module | VK | Completed | 2019-07-10

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2019-09-10 | 61 | 61 | Tasks
2019-09-23 | 61 | 61
2019-09-30 | pp | 28
2019-10-05 | 45 | 47
2019-10-07 | 0 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - All In One Grocery
SB2/US1 | As a buyer I want to select the self pickup option so that I can select the pickup delivery type | SB2/US1/T1 | Designing the GUI for the pickup button. | RS | Completed | 2019-07-10
|  | SB2/US1/T2 | Connection with database to insert the data | VK | Completed | 2019-07-10
|  | SB2/US1/T3 | Testing of the module on localhost and then on server. | RB | Completed | 2019-07-10
SB2/US2 | As a buyer I want to select address from saved address so that I can select delivered to this option | SB2/US2/T1 | Designing of GUI | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US2/T2 | Connection with Database to fetch the record. | RS | Completed | 2019-07-10
|  | SB2/US2/T3 | Displaying the fetched data on screen. | VK | Completed | 2019-07-10
|  | SB2/US2/T4 | Selecting the address on click. | RB | Completed | 2019-07-10
|  | SB2/US2/T5 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 2019-07-10
SB2/US3 | As a Buyer I want to add new delivery address so that I can add new address | SB2/US3/T1 | Designing the GUI for the Add Address button. | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US3/T2 | Connection with database to insert the data. | RS | Completed | 2019-07-10
|  | SB2/US3/T3 | Testing of the module on localhost and then on server. | VK | Completed | 2019-07-10
SB2/US4 | As a buyer I want to place a order so that I can get the products | SB2/US4/T1 | Designing of GUI for placing the order button. | RB | Completed | 2019-07-10
|  | SB2/US4/T2 | Validating user input at client level | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US4/T3 | Validating user input at server level | RS | Completed | 2019-07-10
|  | SB2/US4/T4 | Connection with Database to insert the record. | VK | Completed | 2019-07-10
|  | SB2/US4/T5 | Testing of the module on localhost and then on server. | RB | Completed | 2019-07-10
SB2/US5 | As a buyer I want to see the thank you page so that I can assure my product confirmation | SB2/US5/T1 | Designing of Thank You page. | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US5/T2 | Send Email via coding using the Mandrill App | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US5/T3 | Connection with database to insert the order details in the database. | RS | Completed | 2019-07-10
|  | SB2/US5/T4 | Testing of the module on localhost and then on server. | VK | Completed | 2019-07-10
SB2/US6 | As a buyer I want to receive the order details in mail so that I have a proof of order | SB2/US6/T1 | Designing of format of email (to be sent). | RB | Completed | 2019-07-10
|  | SB2/US6/T2 | Validating user input at client level | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US6/T3 | Validating user input at server level | RS | Completed | 2019-07-10
|  | SB2/US6/T4 | Testing of the module on localhost and then on server. | VK | Completed | 2019-07-10
SB2/US7 | As a buyer I want to remove product from cart so that I can delete the product from cart if no longer required | SB2/US7/T1 | Designing of GUI for Remove Product button. | RB | Completed | 2019-07-10
|  | SB2/US7/T2 | Connection with Database to update the status of the cart. | RS+RB+VK | Completed | 2019-07-10
|  | SB2/US7/T3 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 2019-07-10
SB2/US8 | As a buyer I see the subtotal of each item in cart so that I can see the cost of each item | SB2/US8/T1 | Connection with Database to fetch the status of the cart. | RS | Completed | 13/10/2019
|  | SB2/US8/T2 | Displaying the fetched data on screen. | VK | Completed | 13/10/2019
|  | SB2/US8/T3 | Displaying the total cost for all the items in the cart. | RB | Completed | 13/10/2019
|  | SB2/US8/T4 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 13/10/2019
SB2/US9 | As a buyer I want to see the banner area at home page so that I can see the special offers | SB2/US9/T1 | Connection with Database to fetch all the offers and discounts. | RS | Completed | 13/10/2019
|  | SB2/US9/T2 | Designing of GUI. | VK | Completed | 13/10/2019
|  | SB2/US9/T3 | Adding link to offers so that we can go on products page. | RB | Completed | 13/10/2019
|  | SB2/US9/T4 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 13/10/2019
SB2/US10 | As a buyer I want to see the logout button so that I can logout from the logout | SB2/US9/T1 | Designing of GUI for LogOut button. | RS+RB+VK | Completed | 13/10/2019
|  | SB2/US9/T2 | Testing of the module on localhost and then on server. | RS | Completed | 13/10/2019
SB2/US11 | As a buyer I want to see the hot offers on home page so that I can see the currently running offer in the store | SB2/US10/T1 | Connection with Database to fetch all the offers and discounts. | VK | Completed | 13/10/2019
|  | SB2/US10/T2 | Designing of GUI. | RB | Completed | 13/10/2019
|  | SB2/US10/T3 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 13/10/2019
SB2/US12 | As a DBA I want to create database so that I can store all the customer information to serve customer better | SB2/US11/T1 | Creating a database for storing all the records. | RS | Completed | 13/10/2019
|  | SB2/US11/T2 | Creating specified tables in tha database for particular entities. | VK | Completed | 13/10/2019
|  | SB2/US11/T3 | Connection with Database to fetch all the offers and discounts. | RB | Completed | 13/10/2019
SB2/US13 | As a DBA I want to fire select query so that I can view the records | SB2/US12/T1 | Connection with Database . | RS+RB+VK | Completed | 13/10/2019
|  | SB2/US12/T2 | Writing a select query to fetch the specific records. | RS+RB+VK | Completed | 13/10/2019
|  | SB2/US12/T3 | Testing of the module on localhost and then on server. | RS | Completed | 13/10/2019
SB2/US14 | As a DBA I want to fire update query so that I can keep the database updated | SB2/US14/T1 | Connection with Database . | VK | Completed | 14/10/2019
|  | SB2/US14/T2 | Writing a update query to update the specific records. | RB | Completed | 14/10/2019
|  | SB2/US14/T3 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 14/10/2019
SB2/US15 | As a DBA I want to fire delete query so that I can remove unwanted of faulty data from databaser | SB2/US15/T1 | Connection with Database . | RS | Completed | 14/10/2019
|  | SB2/US15/T2 | Writing a delete query to delete the specific unrequired records. | VK | Completed | 14/10/2019
|  | SB2/US15/T3 | Testing of the module on localhost and then on server. | RB | Completed | 14/10/2019

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-04 | 177 | 190 | Tasks
2017-09-18 | 110 | 150
2017-09-25 | 80 | 100
2017-10-02 | 66 | 65
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - All In One Grocery
SB3/US1 | As a DBA I want to take backup so that I can save all the old records for security purpose | SB3/US1/T1 | Validating user input | RS | Completed | 23/12/2019
|  | SB3/US1/T2 | Connection with database to backup the record. | VK | Completed | 23/12/2019
|  | SB3/US1/T3 | Testing of the module on localhost and then on server. | RB | Completed | 23/12/2019
SB3/US2 | As a DBA I want to delete old backup si that I can delete the records which are not needed any more | SB3/US2/T1 | Validating user input | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US2/T2 | Submitting form and getting the data | RS | Completed | 23/12/2019
|  | SB3/US2/T3 | Connection with database to delete the record. | VK | Completed | 23/12/2019
|  | SB3/US2/T4 | Testing of the module on localhost and then on server. | RB | Completed | 23/12/2019
SB3/US3 | As a admin I want to login into the admin panel using given credentials so that I can access the admin panel | SB3/US3/T1 | Designing of GUI | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US3/T2 | Validating user input | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US3/T3 | Submitting form and getting the data | RS | Completed | 23/12/2019
|  | SB3/US3/T4 | Connection with database to login. | VK | Completed | 23/12/2019
SB3/US4 | As a admin I want to see the error in login so that I can I can enter the correct credentials | SB3/US4/T1 | Designing the GUI | RB | Completed | 23/12/2019
|  | SB3/US4/T2 | Validating user input | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US4/T3 | Connection with database to check the error in login.. | RS | Completed | 23/12/2019
|  | SB3/US4/T4 | Show error message if not able to login | VK | Completed | 23/12/2019
|  | SB3/US4/T5 | Testing of the module on localhost and then on server. | RB | Completed | 23/12/2019
SB3/US5 | As a admin I want to see the homepage of admin panel so that I can access the general content of admin | SB3/US5/T1 | Designing the GUI | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US5/T2 | Validate user input at client level & server level. | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US5/T3 | Connection with database to login into admin panel. | RS | Completed | 23/12/2019
|  | SB3/US5/T4 | Testing of the module on localhost and then on server. | VK | Completed | 23/12/2019
SB3/US6 | As a admin I want to see the list of all the order so that I can prepare the order | SB3/US6/T1 | Designing the GUI | RB | Completed | 23/12/2019
|  | SB3/US6/T2 | Validate user input at client level & server level. | RS+RB+VK | Completed | 23/12/2019
|  | SB3/US6/T3 | Connection with database to view list of all orders.. | RS | Completed | 23/12/2019
|  | SB3/US6/T4 | Testing of the module on localhost and then on server. | VK | Completed | 23/12/2019
SB3/US7 | As a admin I want to see the specific items ordered so that I can prepare order specifically | SB3/US7/T1 | Designing the GUI | RB | Completed | 29/12/2019
|  | SB3/US7/T2 | Validate user input at client level & server level. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US7/T3 | Connection with database to view specific list of orders.. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US7/T4 | Testing of the module on localhost and then on server. | RS | Completed | 29/12/2019
SB3/US8 | As a admin I want to see the total amount to be collected so that I can collect that amount from customer at the time of delivery | SB3/US8/T1 | Designing the GUI | VK | Completed | 29/12/2019
|  | SB3/US8/T2 | Validate user input at client level & server level. | RB | Completed | 29/12/2019
|  | SB3/US8/T3 | Connection with database to view total amount to be collected. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US8/T4 | Testing of the module on localhost and then on server. | RS | Completed | 29/12/2019
SB3/US9 | As a admin I want to see the type of order so that I can collect that amount from customer | SB3/US9/T1 | Designing the GUI | VK | Completed | 29/12/2019
|  | SB3/US9/T2 | Validate user input at client level & server level. | RB | Completed | 29/12/2019
|  | SB3/US9/T3 | Connection with database to view type of orders. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US9/T4 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 29/12/2019
SB3/US10 | As a admin see all the products present in database so that I can update the details | SB3/US10/T1 | Designing the GUI | RS | Completed | 29/12/2019
|  | SB3/US10/T2 | Connection with database to view all products available. | VK | Completed | 29/12/2019
|  | SB3/US10/T3 | Testing of the module on localhost and then on server. | RB | Completed | 29/12/2019
SB3/US11 | As a admin I want to filter the products category wise so that I can see the products of particular category | SB3/US11/T1 | Designing the GUI | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US11/T2 | Connection with database to view filtered products category wise. | RS | Completed | 29/12/2019
|  | SB3/US11/T3 | Testing of the module on localhost and then on server. | VK | Completed | 29/12/2019
SB3/US12 | As a admin I want to edit the product details so that customer can see the latest details of the product | SB3/US12/T1 | Designing the GUI | RB | Completed | 29/12/2019
|  | SB3/US12/T2 | Validate user input at client level & server level. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US12/T3 | Connection with database to edit product details. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US12/T4 | Testing of the module on localhost and then on server. | RS | Completed | 29/12/2019
SB3/US13 | As a admin I want to delete the product from the database so that customer cannot see the unwanted data | SB3/US13/T1 | Designing the GUI | VK | Completed | 29/12/2019
|  | SB3/US13/T2 | Validate user input at client level & server level. | RB | Completed | 29/12/2019
|  | SB3/US13/T3 | Connection with database to delete product details. | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US13/T4 | Testing of the module on localhost and then on server. | RS | Completed | 29/12/2019
SB3/US14 | As a admin I want to see the successfully updated message after product details updated successfully so that I can assure that product details are updated | SB3/US14/T1 | Designing the GUI | VK | Completed | 29/12/2019
|  | SB3/US14/T2 | Connection with database to see updated product details. | RB | Completed | 29/12/2019
|  | SB3/US14/T3 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 29/12/2019
SB3/US15 | As a admin I want to see the successfully deleted message after product deleted successfully so that I can assure that product is deleted from the database | SB3/US15/T1 | Designing the GUI | RS+RB+VK | Completed | 29/12/2019
|  | SB3/US15/T2 | Connection with database to see message of deleted product details. | RB | Completed | 29/12/2019
|  | SB3/US15/T3 | Testing of the module on localhost and then on server. | VK | Completed | 29/12/2019

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-10-12 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 17
2017-11-01 | 15 | 15
2017-11-02 | 0 | 0
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - All In One Grocery
SB4/US1 | As a Admin I want to add a new product so that customer can see the newly added product | SB4/US1/T1 | Designing the GUI | RS | Completed | 2020-10-01
|  | SB4/US1/T2 | Validate user input at client level & server level. | VK | Completed | 2020-10-01
|  | SB4/US1/T3 | Connection with database to add the product in the database. | RB | Completed | 2020-10-01
|  | SB4/US1/T4 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 2020-10-01
SB4/US2 | As a Admin I want to upload image of the product so that I customer can see the image of products | SB4/US2/T1 | Designing the GUI | RS | Completed | 2020-10-01
|  | SB4/US2/T2 | Validate user input at client level & server level. | VK | Completed | 2020-10-01
|  | SB4/US2/T3 | Connection with database to check the details of product. | RB | Completed | 2020-10-01
|  | SB4/US2/T4 | Connection with database to upload the image in the database. | RS+RB+VK | Completed | 2020-10-01
|  | SB4/US2/T5 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 2020-10-01
SB4/US3 | As a Admin I want to see the successfully added product message after product added successfully so that I can assure that product is added in database | SB4/US3/T1 | Designing the GUI | RS | Completed | 2020-10-01
|  | SB4/US3/T2 | Connection with database to check the details of product. | VK | Completed | 2020-10-01
|  | SB4/US3/T3 | Testing of the module on localhost and then on server. | RB | Completed | 2020-10-01
SB4/US4 | As a Admin I want to add new category I can add products in that category | SB4/US4/T1 | Designing the GUI | RS+RB+VK | Completed | 2020-10-01
|  | SB4/US4/T2 | Connection with database to add new category of the product. | RS | Completed | 2020-10-01
|  | SB4/US4/T3 | Validate user input at client level. | VK | Completed | 2020-10-01
|  | SB4/US4/T4 | Validate user input at server level. | RB | Completed | 2020-10-01
|  | SB4/US4/T5 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 2020-10-01
SB4/US5 | As a Admin I want to see the successfully added product category message after category added successfully so that I can assure that category is added in database | SB4/US5/T1 | Designing the GUI of the message. | RS+RB+VK | Completed | 2020-10-01
|  | SB4/US5/T2 | Validate user input at client level & server level. | RS | Completed | 2020-10-01
|  | SB4/US5/T3 | Connection with database to check the category of product. | VK | Completed | 2020-10-01
|  | SB4/US5/T4 | Testing of the module on localhost and then on server. | RB | Completed | 2020-10-01
SB4/US6 | As a Admin I want to delete category so that deleted category is no longer visible in the website/app | SB4/US6/T1 | Designing the GUI | RS+RB+VK | Completed | 27/1/2020
|  | SB4/US6/T2 | Validate user input at client level & server level. | RS | Completed | 27/1/2020
|  | SB4/US6/T3 | Connection with database to delete the category of product. | VK | Completed | 27/1/2020
|  | SB4/US6/T4 | Testing of the module on localhost and then on server. | RB | Completed | 27/1/2020
SB4/US7 | As a Admin I want to see the successfully deleted category message after category deleted successfully so that I can assure that category is deleted from database | SB4/US7/T1 | Designing the GUI of the message. | RS+RB+VK | Completed | 27/1/2020
|  | SB4/US7/T2 | Validate user input at client level & server level. | RS+RB+VK | Completed | 27/1/2020
|  | SB4/US7/T3 | Connection with database to check the category of deleted product. | RS | Completed | 27/1/2020
|  | SB4/US7/T4 | Testing of the module on localhost and then on server. | VK | Completed | 27/1/2020
SB4/US8 | As a Admin I want to see all the users in the website so that I can see the list of users | SB4/US8/T1 | Designing the GUI | RB | Completed | 27/1/2020
|  | SB4/US8/T2 | Connection with database to check the details of all the products. | RS+RB+VK | Completed | 27/1/2020
|  | SB4/US8/T3 | Load all data from the database. | RS | Completed | 27/1/2020
|  | SB4/US8/T4 | Testing of the module on localhost and then on server. | VK | Completed | 27/1/2020
SB4/US9 | As a Developer I want to create android project so that I can android application of that product | SB4/US9/T1 | Understanding the components of Android Studio. | RB | Completed | 27/1/2020
|  | SB4/US9/T2 | Install Android Studio. | RS+RB+VK | Completed | 27/1/2020
|  | SB4/US9/T3 | Start Writing the code. | RS+RB+VK | Completed | 27/1/2020
|  | SB4/US9/T4 | Testing of the module on real device. | RS | Completed | 27/1/2020
SB4/US10 | As a Developer I want to create WebView in android application project so that I can create webview of product | SB4/US10/T1 | Designing the GUI | VK | Completed | 2020-10-02
|  | SB4/US10/T2 | Connection of Android project with database | RB | Completed | 2020-10-02
|  | SB4/US10/T3 | Validate user at client level & server level. | RS+RB+VK | Completed | 2020-10-02
|  | SB4/US10/T4 | Testing of the module on localhost and then on server. | RS | Completed | 2020-10-02
SB4/US11 | As a Developer I want to create Splash Screen so that customer do not see blank page | SB4/US11/T1 | Designing the GUI | VK | Completed | 2020-10-02
|  | SB4/US11/T2 | Connection with database to load data. | RB | Completed | 2020-10-02
|  | SB4/US11/T3 | Check whether data is successfully loaded | RS+RB+VK | Completed | 2020-10-02
|  | SB4/US11/T4 | Testing of the module on localhost and then on server. | RS+RB+VK | Completed | 2020-10-02
SB4/US12 | As a Developer I want to upload the android application to playstore so that user can download the application | SB4/US12/T1 | Buy the developer server to upload app on playstore. | RS | Completed | 2020-10-02
|  | SB4/US12/T2 | Complete the credentials to upload the application. | VK | Completed | 2020-10-02
|  | SB4/US12/T3 | Upload The application. | RB | Completed | 2020-10-02
|  | SB4/US12/T4 | Maintain the application. | RS+RB+VK | Completed | 2020-10-02
SB4/US13 | As a Buyer I want to install the android application so that I can do all the work in mobile device | SB4/US13/T1 | Open Playstore | RS | Completed | 2020-10-02
|  | SB4/US13/T2 | Download the application | VK | Completed | 2020-10-02
|  | SB4/US13/T3 | Open the application. | RB | Completed | 2020-10-02
SB4/US14 | As a Buyer I want to order the product via android application so that I can order the product by mobile | SB4/US14/T1 | Open the application. | RS+RB+VK | Completed | 2020-10-02
|  | SB4/US14/T2 | Login into the application. | RS+RB+VK | Completed | 2020-10-02
|  | SB4/US14/T3 | Buy the desired product. | RB | Completed | 2020-10-02
|  | SB4/US14/T4 | Logout of the application successfully. | VK | Completed | 2020-10-02

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2017-10-12 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 16
2017-11-01 | 15 | 15
2017-11-02 | 0 | 0
0
Days