## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Buyer | Access the website/app | I Can see the product listing | 1 | RP
1 | SB1/US2 | Buyer | See all the products | I Can see the variety of the products | 1 | VK
1 | SB1/US3 | Buyer | Search the product through search bar | I Can Search the choice of product by keyword | 1 | RB
1 | SB1/US4 | Buyer | View The Cart | I Can See The Products which are available in my cart | 1 | DM
1 | SB1/US5 | Buyer | Login | I can see my saved content | 1 | RJ
1 | SB1/US6 | Buyer | Signup | I Can Keep My address details saved | 1 | PM
1 | SB1/US7 | Buyer | Contact to service provider | I can send a query | 1 | DM
1 | SB1/US8 | Buyer | See the product category wise | I Can see the product category wise | 1 | RJ
1 | SB1/US9 | Buyer | to add a product in my cart | I Can place a order | 1 | PM
1 | SB1/US10 | Buyer | to update a product quantity inside a cart | I Can change the quantity of the product in cart | 1 | DM
1 | SB1/US11 | Buyer | to delete a product inside a cart | I Can change the remove the product in cart | 1 | DM
1 | SB1/US12 | Buyer | to see the cart total | I Can See the total amount of product which I have added in cart | 1 | RJ
1 | SB1/US13 | Buyer | to See the specific product detail | I Can check the details of the specific product | 1 | PM
1 | SB1/US14 | Buyer | to go to checkout | I Can select type of method of delivery | 1 | DM
1 | SB1/US15 | Buyer | See the order summery at checkout page | I Can see the products which I have added in cart | 1 | RJ
2 | SB2/US1 | Buyer | select the self pickup option | I Can select pickup delivery option | 1 | PM
2 | SB2/US2 | Buyer | select address from saved addresses | I Can select delivered to this address option | 1 | DM
2 | SB2/US3 | Buyer | add new delivery address | I Can add new address | 1 | RJ
2 | SB2/US4 | Buyer | see the thank you page | I Can assure my product confirmation | 1 | PM
2 | SB2/US5 | Buyer | receive the order details in main | I have a proof of order | 1 | DM
2 | SB2/US6 | Buyer | Remove product from cart | I Can delete the product from cart if no longer required | 1 | RJ
2 | SB2/US7 | Buyer | See the sub total of each item | I Can see the cost of each item | 1 | PM
2 | SB2/US8 | Buyer | See the banner area at home page | I Can see the special offers | 1 | DM
2 | SB2/US9 | Buyer | See the logout button | I Can logout from the website | 1 | DM
2 | SB2/US10 | Buyer | See the hot offers on home page | I Can see the currently running offer in the store | 1 | DM
2 | SB2/US11 | DBA | Create database | I Can store all customer information to serve customer better | 1 | DM
2 | SB2/US12 | DBA | Fire Select Queries | I Can View The Records | 1 | DM
2 | SB2/US13 | DBA | Fire Update Queries | I Can Keep The Database Updated | 1 | RJ
2 | SB2/US14 | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data | 1 | PM
2 | SB2/US15 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use | 1 | DM
3 | SB3/US1 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 1 | RJ
3 | SB3/US2 | Admin | Login Into The System Using given credentials | I Can Access The Admin panel | 2 | PM
3 | SB3/US3 | Admin | See the error in login | I Can Enter the correct credentials | 2 | DM
3 | SB3/US4 | Admin | See list of all the orders | I can prepare the order | 2 | RJ
3 | SB3/US5 | Admin | See the specific items ordered | I can prepare order specifically | 2 | PM
3 | SB3/US6 | Admin | See the total amount to be collected | I can collect that amount from customer | 2 | DM
3 | SB3/US7 | Admin | See the type of order | I Can deliver the order accordingly | 2 | RJ
3 | SB3/US8 | Admin | See all the products present in database | I can update the details | 2 | PM
3 | SB3/US9 | Admin | Filter the product category wise | I Can see the products of particular category | 2 | DM
3 | SB3/US10 | Admin | Edit product details | Customer can see the latest details of the product | 2 | RJ
3 | SB3/US11 | Admin | Delete the product from the database | Customer cannot see the unwanted product | 2 | PM
3 | SB3/US12 | Admin | See the successfully updated message after product updated sucessfully | I Can assure that product details is updated | 2
3 | SB3/US13 | Admin | See the successfully deleted message after product deleted sucessfully | I Can assure that product is deleted from the database | 2
3 | SB3/US14 | Admin | Add a new product | Customer can see the newly added product | 2
3 | SB3/US15 | Admin | Upload image of the product | Customer can see the image of the newly added product also | 2
4 | SB4/US1 | Admin | See the successfully added product message after product added sucessfully | I Can assure that product is added in database | 2
4 | SB4/US2 | Admin | Add new category | I can add products in that category | 3
4 | SB4/US3 | Admin | See the successfully added category message after category added sucessfully | I Can assure that category is added in database | 3
4 | SB4/US4 | Admin | Delete category | Category is no longer visible in the website/app | 3
4 | SB4/US5 | Admin | See the successfully deleted category message after category deleted sucessfully | I Can assure that category is deleted from database | 3
4 | SB4/US6 | Admin | All the users in the website | I can see the list of users | 3
4 | SB4/US7 | Developer | Create android project | I can develop webview | 3
4 | SB4/US8 | Developer | Webview in android application project | I can develop application | 3
4 | SB4/US9 | Developer | Splash screen | Customer do not see blank page | 3
4 | SB4/US10 | Buyer | I want to install the android application | I Can do all the work in android phone | 3
4 | SB4/US11 | Buyer | I want to order the product via android application | I Can order the product by mobile | 3
4 | SB4/US12
4 | SB4/US13
4 | SB4/US14
4 | SB4/US15

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - All In One Grocery
SB1/US1 | Aa a Buyer | SB1/US1/T1 | Study of (Bootstrap+Struts 2.0) | RA+SP+PB+RM | Completed | 2019-08-21
|  | SB1/US1/T2 | Designing of GUI | PB | In Progress | 2019-08-21
|  | SB1/US1/T3 | Validating user input at client level | RA | Not Started | 2019-08-21
|  | SB1/US1/T4 | Validating user input at server level | SP | Completed | 2019-08-21
|  | SB1/US1/T5 | Connection with Database to insert the record. | RM | In Progress | 2019-08-21
|  | SB1/US1/T6 | Testing of the module on localhost and then on server. | RA+SP+PB+RM | Not Started | 2019-08-21
SB1/US2 | Aa a Buyer | SB1/US2/T1 | Study of Mandrill App to send email | RA+SP+PB+RM
|  | SB1/US2/T2 | Designing of Email(to be send) | PB
|  | SB1/US2/T3 | Send Email via coding using the Mandrill App | SP
|  | SB1/US2/T4 | Connection with database to update the status in the database. | RA
|  | SB1/US2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US3 | Aa a Buyer | SB1/US3/T1 | Designing the GUI | SP
|  | SB1/US3/T2 | Validate user input at Client Level & server level. | RA
|  | SB1/US3/T3 | Check user valid or not (connecting the database) | RM
|  | SB1/US3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US4 | Aa a Buyer |  | Designing the GUI | SP
|  |  | Validate user input at Client Level & server level. | PB
|  |  | Connection with database to check the old password | RA
|  |  | Connection with database to update the status in the database. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US5 | Aa a Buyer |  | Designing the GUI | SP
|  |  | Validate user input at Client Level & server level. | PB
|  |  | Connection with database to update the status in the database. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US6 | Aa a Buyer |  | Designing of GUI | PB
|  |  | Validating user input at client level | RA
|  |  | Validating user input at server level | SP
|  |  | Connection with Database to insert the record. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US7 | Aa a Buyer |  | Designing of Email(to be send) | PB
|  |  | Send Email via coding using the Mandrill App | SP
|  |  | Connection with database to update the status in the database. | RA
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US8 | Aa a Buyer |  | Designing the GUI | SP
|  |  | Validate user input at Client Level & server level. | RA
|  |  | Check user valid or not (connecting the database) | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US9 | Aa a Buyer |  | Designing the GUI | SP
|  |  | Validate user input at Client Level & server level. | PB
|  |  | Connection with database to check the old password | RA
|  |  | Connection with database to update the status in the database. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US10 | Aa a Buyer |  | Designing of GUI | PB
|  |  | Validating user input at client level | RA
|  |  | Validating user input at server level | SP
|  |  | Connection with Database to insert the record. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US11 | Aa a Buyer |  | Designing of Email(to be send) | PB
|  |  | Send Email via coding using the Mandrill App | SP
|  |  | Connection with database to update the status in the database. | RA
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US12 | Aa a Buyer |  | Designing the GUI | SP
|  |  | Validate user input at Client Level & server level. | RA
|  |  | Check user valid or not (connecting the database) | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US13 | Aa a Buyer |  | Designing the GUI | SP
|  |  | Validate user input at Client Level & server level. | PB
|  |  | Connection with database to check the old password | RA
|  |  | Connection with database to update the status in the database. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US14 | Aa a Buyer |  | Designing of GUI | PB
|  |  | Validating user input at client level | RA
|  |  | Validating user input at server level | SP
|  |  | Connection with Database to insert the record. | RM
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM
SB1/US15 | Aa a Buyer |  | Designing of Email(to be send) | PB
|  |  | Send Email via coding using the Mandrill App | SP
|  |  | Connection with database to update the status in the database. | RA
|  |  | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2017-08-14 | 132 | 170 | Tasks
2017-08-21 | 120 | 110
2017-08-28 | 80 | 120
2017-09-04 | 56 | 55
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 |  | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
|  | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-04 | 177 | 190 | Tasks
2017-09-18 | 110 | 150
2017-09-25 | 80 | 100
2017-10-02 | 66 | 65
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-10-12 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 17
2017-11-01 | 15 | 15
2017-11-02 | 0 | 0
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2017-10-12 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 16
2017-11-01 | 15 | 15
2017-11-02 | 0 | 0
0
Days